## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Machine Learning
INTERN NAME: | Dhananjay Gaur
PROJECT NAME: | PlacementPal : Graduation and Placement Predictor
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2023-05-08
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | PlacementPal : Graduation and Placement Predictor
PROJECT ID
PROJECT MANAGER | HARSHADA TOPALE
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
Create backup plans for essential components, and broaden your vendor options. | MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2023-08-05 | Scope Creep | Scope Management | NO | Put in place stricter change management practices. Every modification request needs to be tracked down and evaluated in terms of how it will affect the project's budget and schedule. | Procedures for managing change have been implemented. | Project Manager | SOLVED | Changes to the scope are now carefully documented and their effects are assessed before approval.
2 | 2023-08-06 | Resource Shortage | Resource Management | YES | Conduct a thorough analysis of resource allocation during project planning. Keep the team members' workloads manageable. | Resource distribution has changed. | Project Manager | SOLVED | Team members' responsibilities have been evenly distributed, and output has grown.
3 | 2023-08-12 | Communication Breakdown | Communication | YES | Set up regular team meetings and open channels of communication. | It has been decided to hold weekly team meetings. | Team Lead | SOLVED
4 | 2023-08-15 | Vendor Delay | Procurement | YES | Create backup plans for essential components, and broaden your vendor options. | The providers of backups have been located. | Procurement Manager | SOLVED
5 | 2023-08-20 | Quality Control Issue | Quality Management | NO | Develop a detailed quality control plan that includes regular testing and inspections. | A quality assurance check list was used. | QA Manager | SOLVED
6 | 2023-08-24 | Stakeholder Misalignment | Stakeholder Management | NO | Interviewing important stakeholders will help you develop a clear communication plan. | A clear strategy for interacting with stakeholders. | Project Manager | SOLVED | Stakeholder involvement has increased, and expectations are being met more successfully.
7 | 2023-08-26 | Technology Compatibility | Technical | YES | Considerably examine and evaluate compatibility with legacy systems during the planning phase. | It was tested for compatibility. | Tech Lead | SOLVED
8 | 2023-09-01 | Team Training | Skills Development | YES | Provide training and tools for skill development before starting efforts with new technologies. | Training events were scheduled. | HR Manager | SOLVED
9 | 2023-09-06 | Change Resistance | Change Management | YES | Implement a stakeholder- and clear communication-focused change management plan. | It was decided to hold workshops on change management. | Change Manager | SOLVED | There is less resistance to change now, and process improvements are encouraged.
10 | 2023-09-10 | Budget Overrun | Financial | NO | Create a reliable technique for managing your budget, and evaluate it frequently. | Budget tracking software has been implemented. | Finance Manager | SOLVED