## Sheet1
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | PlacementPal : Graduation and Placement Predictor
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Excel Sheet of Results of Prediction Model
PROJECT SCOPE
PROJECT START DATE | 2023-08-01
PROJECT END DATE | 2023-09-16
OVERALL PROGRESS | Completed
S.No | Task Name | Assigned To | Start Date | End Date | Duration in Days | STATUS
1 | Initiation
1.1 | Assess the root cause of the business problem. |  | 2023-08-01 | 2023-08-03 | 3 | COMPLETED
1.2 | Recruit a team |  | 2023-08-01 | 2023-08-03 | 3 | COMPLETED
1.3 | Create a project charter |  | 2023-08-01 | 2023-08-03 | 3 | COMPLETED
1.4 | Requirement gathering |  | 2023-08-01 | 2023-08-03 | 3 | COMPLETED
2 | Planning
2.1 | Baseline Project Plan |  | 2023-08-05 | 2023-08-09 | 5 | COMPLETED
2.2 | Create Work Breakdown Structure |  | 2023-08-05 | 2023-08-09 | 5 | COMPLETED
2.3 | Maintaining RAID Logs |  | 2023-08-05 | 2023-08-09 | 5 | COMPLETED
3 | Execution
3.1 | Finalise Design |  | 2023-08-12 | 2023-08-20 | 8 | COMPLETED
3.2 | Build |  | 2023-08-22 | 2023-09-10 | 19 | COMPLETED
3.2.1 | Data Cleaning |  | 2023-08-23 | 2023-08-23 | 1 | COMPLETED
3.2.2 | Testing different Classification Models |  | 2023-08-25 | 2023-08-25 | 1 | COMPLETED
3.2.3 | Selection of Classification Model |  | 2023-08-26 | 2023-08-26 | 1 | COMPLETED
3.2.4 | Traning of selected model |  | 2023-08-29 | 2023-08-29 | 1 | COMPLETED
3.2.5 | Analysis of obtained results |  | 2023-08-31 | 2023-08-31 | 1 | COMPLETED
3.2.6 | Selection of Regression Model |  | 2023-09-04 | 2023-09-04 | 1 | COMPLETED
3.2.7 | Analysis of Regression Results |  | 2023-09-07 | 2023-09-07 | 1 | COMPLETED
3.3 | Testing |  | 2023-09-10 | 2023-09-10 | 1 | COMPLETED
4 | Deployment |  | 2023-09-10 | 2023-09-10 | 1 | COMPLETED
5 | Closure |  | 2023-09-11 | 2023-09-16 | 6 | COMPLETED
5.1 | Project Report Generation |  | 2023-09-11 | 2023-09-13 | 3 | COMPLETED
5.2 | Lessons Learnt Logs Generation |  | 2023-09-14 | 2023-09-16 | 3 | COMPLETED
COMPLETED