## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 0 | 2 | 1 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | PlacementPal : Graduation and Placement Predictor |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 1 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2023-09-17 | Project Team Lead: | Dhananjay Gaur |  |  | Dependency | 2 | 0 | 1 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 9 |  |  |  |  | 5
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Delay in doing critical maintenance. | the effect on the project's budget and schedule. | For the project, form a team for upkeep.Consideration should be given to the project budget. | Project Manager | High |  | Open | Risk
2 | Risk | Long supply delivery times | Impact on project schedule | Look for suppliers who can deliver the requested resources on schedule and within the estimated cost. | Project Manager | Critical |  | Closed | Assumption
3 | Risk | Missing data | Impact on project schedule and performance | Data recovery procedures will be implemented, and frequent data backups will be carried out. | IT Team | High | 12 | Open | Issue
4 | Assumption | There are readily available key employees. | The impact on the project's timeline and budget. | The initiative anticipates that key team members will always be accessible. Contingency plans have been made in case of unanticipated absences. | Project Manager | Moderate |  | Open | Dependency
5 | Issue | Budget Overflow | The impact on the project's timeline and budget. | Continuous monitoring of project expenditures will be performed, and if necessary, scope revisions or extra financing requests will be made. | Finance Team | High |  | Closed
6 | Dependency | Critical Component Delivery from a Vendor | Impact on project schedule | Close engagement with the vendor and regular status checks are required. Plan for escalation in the event of a delay. | Project Manager | High |  | Closed | Open
7 | Risk | Scope Creep | impact on the performance and timeline of a project | There are strict change control processes in place. The Change Control Board must approve any scope adjustments. | Project Manager | Moderate | 8 | Open | Closed
8 | Assumption | Hardware Availibility | Impact on project cost | The essential hardware is anticipated to be available when needed. A buffer of extra hardware has been bought as a precaution. | Procurement Team | Low |  | Closed
9 | Dependency | Availability of Testing Environment | Impact on the performance and timeline of a project | Prior to the testing stages starting, ensuring that the testing environment is prepared. | QA Team | High |  | Open | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24